# CORESHIFT

## Project Planning and Management Plan

### Case Study No. 13 – Migrating a 1.2 Million-Line COBOL Core Banking System

# 1. Introduction

CoreShift is a controlled software reengineering and migration project for a cooperative bank’s legacy core banking system.

The existing system contains approximately 1.2 million lines of COBOL code and has been operational since 1989–2004. Although the system is stable, knowledge of the system is concentrated among only four people, two of whom are expected to retire within the next year. The system also cannot adequately support the instant-payment volumes required by the regulator.

The project will migrate the legacy system toward a modern architecture of approximately 220 KLOC while preserving the exact financial and business behaviour of the existing system.

The most important management objective is to ensure that modernization does not introduce financial discrepancies. Interest calculations, penalties, fees, balances, end-of-day processing and product-specific rules must remain behaviourally equivalent to the legacy system.

Therefore, CoreShift will use an incremental Strangler-Fig migration strategy with parallel running, automated reconciliation, controlled cutover and rollback capability.

# 2. Project Management Objectives

The project will be managed with the following objectives:

- Complete the migration without disrupting critical banking operations.

- Preserve the financial behaviour of the existing COBOL system.

- Capture undocumented knowledge before experienced employees retire.

- Reduce dependency on the existing legacy technology.

- Develop and validate the modern target architecture incrementally.

- Perform extensive parallel testing before production cutover.

- Ensure zero unexplained monetary divergence between legacy and modern systems at final sign-off.

- Maintain complete traceability between requirements, implementation, testing and acceptance.

- Identify and manage technical, operational, financial and schedule risks.

- Maintain a clear rollback mechanism throughout the migration.

- Ensure that all stakeholders know their responsibilities and escalation paths.

- Deliver the project within an approved schedule, effort and budget.

# 3. Project Management Approach

CoreShift will use a hybrid Agile + stage-gate approach.

Agile practices will be used for incremental development, testing and feedback. Stage gates will be used for high-risk banking decisions where formal approval is required.

The project will not use a single big-bang implementation.

Instead, the project will progress through controlled stages:

Reverse Engineering → Requirements Recovery → Architecture Design → Incremental Development → Data Migration → Parallel Run → Reconciliation → Gradual Migration → Controlled Cutover → Stabilization

Each major stage will have defined entry criteria, exit criteria, deliverables and approval authority.

# 4. Project Organization

The major project roles are:

- Project Sponsor

- Project Manager

- Product Owner / Business Lead

- Legacy System Experts

- Business Analysts

- Solution Architect

- Modernization Development Team

- COBOL / Legacy Developers

- Database and Data Migration Team

- QA and Test Team

- Reconciliation / Financial Validation Team

- DevOps / Infrastructure Team

- Security Team

- Compliance and Risk Team

- Operations / Production Support Team

- Release and Change Manager

- Bank Branch / Business Representatives

- External Vendors or Technology Partners, if applicable

# 5. Roles and Responsibilities

## 5.1 Project Sponsor

The Project Sponsor provides executive authority and ensures that the project has adequate organizational support.

### Responsibilities

- Approve the project and major milestones.

- Provide organizational funding and resources.

- Resolve high-level organizational conflicts.

- Approve major scope changes.

- Participate in major go/no-go decisions.

- Approve final production cutover.

- Ensure that business objectives remain aligned with the project.

The Project Sponsor does not manage day-to-day technical activities.

# 5.2 Project Manager

The Project Manager is responsible for overall planning, coordination, monitoring and control.

### Responsibilities

- Create and maintain the project plan.

- Define milestones and schedules.

- Allocate resources.

- Track project progress.

- Conduct project status meetings.

- Maintain the risk and issue registers.

- Monitor dependencies.

- Coordinate different teams.

- Track effort and cost.

- Manage scope changes.

- Escalate critical issues.

- Coordinate cutover planning.

- Ensure that deliverables are completed.

- Report project status to management.

The Project Manager is the central coordination point between technical, business, testing, infrastructure and management teams.

# 5.3 Product Owner / Business Lead

The Product Owner represents the bank’s business requirements.

### Responsibilities

- Define business priorities.

- Confirm expected system behaviour.

- Prioritize migration scope.

- Approve recovered business rules.

- Resolve business ambiguities.

- Validate product-specific behaviour.

- Participate in acceptance testing.

- Approve business readiness for migration.

The Product Owner is particularly important because many rules are undocumented and must be recovered from the legacy system and experienced employees.

# 5.4 Legacy System Experts

The legacy system experts are the four people who currently understand the COBOL system.

They are one of the highest-value and highest-risk resources in the project.

### Responsibilities

- Explain existing COBOL functionality.

- Explain undocumented business rules.

- Explain interest calculations.

- Explain penalty calculations.

- Explain EOD processing.

- Explain product-specific exceptions.

- Explain historical workarounds.

- Validate recovered requirements.

- Support reverse engineering.

- Train replacement team members.

- Participate in knowledge-transfer sessions.

- Validate that the modern implementation preserves legacy behaviour.

### Knowledge Transfer Requirement

Because two experts are expected to retire next year, knowledge transfer must begin immediately.

The project should not wait until the end of development to capture this knowledge.

Each important business area should have:

- Documentation

- Decision tables

- Example inputs and outputs

- Exception cases

- Recorded expert walkthroughs

- At least two trained replacement team members

# 5.5 Business Analysts

Business Analysts convert technical discoveries into documented business requirements.

### Responsibilities

- Interview legacy experts.

- Analyse existing documentation.

- Analyse COBOL behaviour.

- Document business processes.

- Create functional requirements.

- Identify missing or conflicting requirements.

- Create process flows.

- Create decision tables.

- Maintain requirements traceability.

- Coordinate requirement validation with business users.

# 5.6 Solution Architect

The Solution Architect defines the target technical architecture.

### Responsibilities

- Design the modern system architecture.

- Define service boundaries.

- Define API and integration patterns.

- Design the legacy adapter.

- Define database architecture.

- Define reconciliation architecture.

- Ensure scalability.

- Ensure reliability and security.

- Review technical designs.

- Ensure that the architecture supports incremental migration.

The architect is responsible for ensuring that the 82% reduction in LOC does not result in an oversimplified system that loses important business behaviour.

# 5.7 Modernization Development Team

The development team implements the modern system.

### Responsibilities

- Develop modern services.

- Implement recovered business rules.

- Develop APIs.

- Implement interest and penalty calculations.

- Implement account and transaction processing.

- Implement EOD processing.

- Implement product-specific rules.

- Develop integration components.

- Fix defects.

- Write unit and integration tests.

- Support parallel testing.

Development should occur incrementally rather than attempting to rewrite all 1.2 million lines simultaneously.

# 5.8 COBOL / Legacy Developers

Legacy developers support understanding and safe operation of the existing system.

### Responsibilities

- Explain COBOL modules.

- Identify dependencies.

- Explain data structures.

- Support reverse engineering.

- Identify legacy interfaces.

- Explain batch processing.

- Support production investigation when required.

- Validate legacy outputs used as the comparison baseline.

# 5.9 Database and Data Migration Team

The data team is responsible for moving and validating data.

### Responsibilities

- Analyse legacy databases.

- Map legacy data structures to modern structures.

- Develop migration scripts.

- Perform data cleansing where approved.

- Validate migrated data.

- Verify record counts.

- Verify account balances.

- Verify transaction history.

- Verify product mappings.

- Maintain data migration logs.

- Perform migration rehearsals.

- Support rollback and restore testing.

No data transformation should be performed without documented mapping and validation.

# 5.10 QA and Test Team

The QA team is responsible for proving that the modern system behaves correctly.

### Responsibilities

- Prepare the test strategy.

- Create test cases.

- Perform functional testing.

- Perform regression testing.

- Perform integration testing.

- Perform performance testing.

- Perform security testing.

- Perform parallel-run testing.

- Track defects.

- Verify fixes.

- Prepare test reports.

- Support user acceptance testing.

# 5.11 Reconciliation / Financial Validation Team

This role is especially important for CoreShift.

The reconciliation team compares legacy and modern outputs.

### Responsibilities

- Compare account balances.

- Compare interest calculations.

- Compare penalties.

- Compare fees.

- Compare transaction results.

- Compare EOD balances.

- Compare product-specific calculations.

- Identify discrepancies.

- Classify discrepancies.

- Investigate root causes.

- Produce reconciliation reports.

- Confirm that unexplained monetary differences are zero before final approval.

### Reconciliation Classification

Every difference should be classified as:

- Exact Match

- Approved Difference

- Unexplained Difference

An unexplained financial difference must not be ignored.

# 5.12 DevOps / Infrastructure Team

The DevOps team manages the environments required for development, testing, parallel running and production.

### Responsibilities

- Provision environments.

- Configure CI/CD pipelines.

- Manage deployments.

- Monitor infrastructure.

- Configure logging.

- Configure alerts.

- Maintain backups.

- Support disaster recovery.

- Support rollback.

- Maintain production infrastructure.

- Monitor system performance.

# 5.13 Security Team

The Security Team ensures that the modern system protects banking data and transactions.

### Responsibilities

- Security architecture review.

- Identity and access control.

- Encryption review.

- API security.

- Vulnerability assessment.

- Penetration testing.

- Security monitoring.

- Audit logging.

- Incident response planning.

# 5.14 Compliance and Risk Team

The Compliance and Risk Team ensures that migration activities satisfy regulatory and organizational requirements.

### Responsibilities

- Identify compliance requirements.

- Review migration risks.

- Review financial reconciliation policies.

- Participate in go/no-go decisions.

- Review audit evidence.

- Validate controls.

- Ensure appropriate approval for exceptions.

- Confirm that regulatory requirements are not violated during migration.

# 5.15 Operations / Production Support Team

The Operations team takes responsibility for the system after deployment.

### Responsibilities

- Monitor production systems.

- Respond to incidents.

- Monitor transaction failures.

- Monitor reconciliation.

- Support users.

- Execute operational procedures.

- Maintain operational runbooks.

- Support rollback if required.

- Participate in post-cutover stabilization.

# 5.16 Release and Change Manager

The Release and Change Manager controls movement of software between environments.

### Responsibilities

- Maintain release schedules.

- Coordinate deployments.

- Verify release approvals.

- Maintain change records.

- Ensure production changes are authorized.

- Coordinate rollback procedures.

- Prevent unauthorized production changes.

- Maintain release documentation.

# 5.17 Bank Branch / Business Representatives

Business representatives provide real-world validation of system behaviour.

### Responsibilities

- Validate workflows.

- Participate in User Acceptance Testing.

- Validate product behaviour.

- Confirm usability.

- Report business issues.

- Confirm operational readiness.

# 6. Responsibility Matrix

| Activity | Project Manager | Business Lead | Architect | Developers | QA | Data Team | Security | Operations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Planning | A/R | C | C | I | I | I | I | I |
| Requirement Recovery | A | R | C | C | C | I | I | C |
| Reverse Engineering | C | C | R | R | C | C | I | I |
| Architecture | C | C | R | C | C | C | C | C |
| Development | I | C | A | R | C | C | C | I |
| Data Migration | C | C | A | C | C | R | C | C |
| Functional Testing | I | C | C | C | R | C | I | C |
| Reconciliation | C | A | C | C | R | R | I | C |
| Security Testing | I | I | C | C | C | I | R | C |
| Cutover | A | C | R | C | C | C | C | R |
| Rollback | A | C | R | C | C | C | C | R |
| Final Approval | R | R | C | I | C | C | C | C |

Legend:

- R – Responsible: Performs the activity.

- A – Accountable: Owns the final result.

- C – Consulted: Provides input.

- I – Informed: Kept informed of progress.

# 7. Project Phases

The project will be divided into controlled phases.

## Phase 1 – Project Initiation

### Activities

- Confirm project objectives.

- Identify stakeholders.

- Establish project governance.

- Confirm scope.

- Identify initial risks.

- Establish communication channels.

- Create initial project plan.

### Deliverables

- Project Charter

- Stakeholder Register

- Initial Risk Register

- Initial Project Schedule

# 8. Phase 2 – Reverse Engineering

### Activities

- Analyse COBOL source code.

- Identify modules.

- Identify dependencies.

- Analyse database structures.

- Analyse batch jobs.

- Analyse EOD processing.

- Identify interfaces.

- Identify calculations.

- Identify undocumented behaviour.

### Deliverables

- Legacy System Architecture

- COBOL Module Inventory

- Dependency Map

- Business Rule Inventory

- Legacy Data Map

# 9. Phase 3 – Requirements Recovery

### Activities

- Interview the four legacy experts.

- Review existing documentation.

- Analyse system behaviour.

- Record undocumented rules.

- Create decision tables.

- Create functional requirements.

- Validate requirements with business stakeholders.

### Special Priority

Knowledge from the four experts must be captured before the two planned retirements.

### Deliverables

- Recovered Requirements Document

- Business Rules Catalogue

- Decision Tables

- Knowledge Transfer Records

- Requirements Traceability Matrix

# 10. Phase 4 – Target Architecture and Design

### Activities

- Define target architecture.

- Define service boundaries.

- Define database design.

- Design APIs.

- Design legacy adapter.

- Design reconciliation engine.

- Design monitoring architecture.

- Design security controls.

- Prepare UML diagrams.

### Deliverables

- System Architecture

- UML Diagrams

- Database Design

- API Design

- Security Design

- Deployment Design

# 11. Phase 5 – Incremental Development

The modern system will be developed incrementally.

Possible components include:

- Account Service

- Transaction Service

- Interest Service

- Penalty Service

- Product Service

- EOD Processing

- Reconciliation Engine

- Reporting

- Audit and Monitoring

Each component will be independently developed and tested before being integrated into the migration environment.

# 12. Phase 6 – Data Migration

### Activities

- Map legacy fields to modern fields.

- Develop transformation rules.

- Perform trial migration.

- Validate migrated records.

- Compare balances.

- Compare transaction histories.

- Perform reconciliation.

- Correct migration defects.

- Repeat migration rehearsals.

No production migration should occur without a successful rehearsal.

# 13. Phase 7 – Parallel Run

The modern and legacy systems will operate in parallel.

The legacy system will continue to provide the baseline behaviour while the modern system produces corresponding results.

The reconciliation engine will compare:

- Account balances

- Interest

- Penalties

- Fees

- Transactions

- EOD balances

- Product rules

- Status changes

- Rounding behaviour

The project should automate comparison wherever technically feasible.

# 14. Product Type 14 Testing

Product Type 14 contains exactly 30 accounts.

Because the population is only 30 accounts, all 30 accounts will be tested rather than selecting a sample.

The testing approach will therefore be:

30 accounts → 30 legacy outputs → 30 modern outputs → 30 comparisons

Every difference will be investigated.

# 15. Reconciliation Policy

The project will use a strict financial reconciliation policy.

### Required condition for final approval:

Zero unexplained monetary difference.

A one-paisa difference is not automatically considered acceptable.

If a difference is caused by a formally approved rounding or representation rule, it must be documented and approved by the appropriate business, finance/reconciliation and compliance authorities.

Otherwise, it remains an unexplained difference and must be investigated.

# 16. Project Schedule

The COCOMO estimate for approximately 220 KLOC gives an estimated:

- Effort: approximately 1,261 person-months

- Duration: approximately 30.4–30.5 months

- Average staffing: approximately 41 people

These values are estimation references rather than a rigid staffing requirement.

A high-level project schedule can be organized as follows:

| Phase | Approximate Period |
| --- | --- |
| Initiation and Planning | Month 1 |
| Reverse Engineering | Months 1–6 |
| Requirements Recovery | Months 1–7 |
| Architecture and Design | Months 4–9 |
| Incremental Development | Months 7–22 |
| Data Migration Rehearsals | Months 12–23 |
| Parallel Run | Months 18–27 |
| Final Reconciliation | Months 26–29 |
| Controlled Cutover | Month 30 |
| Stabilization | Months 30–31 |

Some activities will overlap.

For example, requirements recovery, reverse engineering, architecture and development should not be treated as completely independent sequential activities.

# 17. Sprint Management

Development work can be organized into approximately two-week sprints.

Each sprint will contain:

- Sprint Planning

- Development

- Code Review

- Unit Testing

- Integration Testing

- Sprint Review

- Defect Fixing

- Retrospective

Each sprint should produce a measurable increment.

Examples:

- Account calculation module completed

- Interest calculation implemented

- Product rules migrated

- API completed

- Reconciliation comparison completed

- EOD calculation validated

# 18. Stage-Gate Management

Certain decisions require formal approval.

## Gate 1 – Requirements Approval

Requirements must be reviewed and approved before major implementation.

## Gate 2 – Architecture Approval

The target architecture must be approved before large-scale development.

## Gate 3 – Migration Readiness

Data migration and technical infrastructure must pass readiness checks.

## Gate 4 – Parallel-Run Approval

Parallel-run results must demonstrate acceptable stability and reconciliation.

## Gate 5 – Cutover Approval

Management must formally approve production cutover.

## Gate 6 – Stabilization Exit

The modern system can become the normal production platform only after the agreed stabilization criteria are satisfied.

# 19. Risk Management

A formal Risk Register will be maintained throughout the project.

Each risk will be scored using:

Risk Score = Probability × Impact

Scale:

- 1 = Very Low

- 2 = Low

- 3 = Medium

- 4 = High

- 5 = Very High

# 20. Major Project Risks

## Risk 1 – Loss of Legacy Knowledge

Probability: 5/5
Impact: 5/5
Risk Score: 25 – Critical

### Mitigation

- Immediate expert interviews.

- Record technical walkthroughs.

- Create decision tables.

- Document undocumented rules.

- Pair legacy experts with replacement engineers.

- Cross-train at least two people per critical business area.

## Risk 2 – Financial Divergence

Probability: 4/5
Impact: 5/5
Risk Score: 20 – High

### Mitigation

- Automated reconciliation.

- Parallel run.

- Exact decimal financial calculations.

- Golden test cases.

- Full comparison wherever technically feasible.

- Product-specific validation.

- Immediate investigation of unexplained differences.

- Rollback capability.

## Risk 3 – Cutover Failure

Probability: 3/5
Impact: 5/5
Risk Score: 15 – High

### Mitigation

- Multiple cutover rehearsals.

- Tested backup and restore.

- Detailed runbook.

- Monitoring.

- Go/no-go checklist.

- Controlled traffic switching.

- Defined rollback triggers.

# 21. Issue Management

A project issue is a problem that has already occurred.

Examples:

- Reconciliation mismatch.

- Failed deployment.

- Missing requirement.

- Data migration error.

- Performance degradation.

- Security vulnerability.

Every issue should contain:

- Issue ID

- Description

- Date identified

- Owner

- Severity

- Business impact

- Root cause

- Corrective action

- Target resolution date

- Current status

# 22. Issue Severity

### Critical

Can cause financial loss, major production failure, regulatory violation or inability to continue migration.

### High

Significant functionality or performance problem that requires urgent action.

### Medium

Important issue that does not immediately stop the project.

### Low

Minor defect or documentation issue.

Critical issues should be escalated immediately to the Project Manager and relevant technical/business authority.

# 23. Change Management

Changes to requirements or architecture must be controlled.

A change request should contain:

- Requested change

- Reason

- Business impact

- Technical impact

- Security impact

- Cost impact

- Schedule impact

- Risk impact

- Approval decision

No major change should be implemented informally.

# 24. Scope Management

## In Scope

- COBOL reverse engineering

- Requirements recovery

- Knowledge transfer

- Modern architecture

- Software reengineering

- Data migration

- Parallel testing

- Reconciliation

- UML and system design

- Risk management

- Cutover planning

- Rollback planning

- Monitoring and audit

## Out of Scope

Unless separately approved:

- Completely redesigning unrelated banking products

- Unrelated branch hardware replacement

- Major organizational restructuring

- Replacing unrelated external banking systems

- Adding new business functionality that is not required for migration

Scope expansion must go through formal change control.

# 25. Communication Management

Communication will occur at multiple levels.

## Daily

Development and technical teams will conduct short daily coordination meetings.

Topics:

- Work completed

- Work planned

- Blockers

- Critical defects

## Weekly

The Project Manager will conduct a weekly project status meeting.

Topics:

- Schedule

- Deliverables

- Risks

- Issues

- Defects

- Reconciliation status

- Resource requirements

## Monthly

Management receives a formal project report.

The report includes:

- Overall progress

- Budget/effort status

- Major milestones

- Major risks

- Critical issues

- Quality metrics

- Migration readiness

# 26. Project Tracking Metrics

The following metrics will be tracked.

### Schedule Metrics

- Planned vs actual progress

- Milestone completion

- Sprint completion rate

- Schedule variance

### Development Metrics

- Features completed

- Code reviewed

- Unit test coverage

- Defects discovered

### Quality Metrics

- Defect density

- Defect severity

- Defect closure rate

- Regression pass rate

- Reconciliation pass rate

### Migration Metrics

- Accounts migrated

- Accounts compared

- Exact matches

- Approved differences

- Unexplained differences

### Knowledge Transfer Metrics

- Expert sessions completed

- Business rules documented

- Modules explained

- Replacement staff trained

# 27. Defect Management

The project will track defects throughout development and testing.

The case study provides:

- Pre-release defects = 310

- Post-release defects = 48

Defect Density:

310 / 220 KLOC = approximately 1.41 defects/KLOC

Defect Removal Efficiency:

310 / (310 + 48) × 100 = approximately 86.6%

These metrics will be used to evaluate the effectiveness of testing and defect removal.

# 28. Cost and Effort Management

The case study provides a COCOMO effort estimate but does not provide actual salary rates, infrastructure costs, licenses or other financial inputs.

Therefore, an exact monetary project cost should not be invented.

The estimated effort is approximately:

1,261 person-months

The monetary cost can be calculated using:

Total Project Cost = Person-Month Effort × Average Cost per Person-Month + Infrastructure + Tools + Licensing + Training + Migration Costs

For example, if the bank provides its fully loaded average cost per person-month, the Project Manager can convert the COCOMO effort into a financial estimate.

# 29. Why LOC Reduction Does Not Equal Effort Reduction

The legacy system contains approximately 1.2 million LOC while the proposed system contains approximately 220 KLOC.

This represents approximately:

81.7% LOC reduction

However, this does not mean that project effort will reduce by 81.7%.

The migration still requires:

- Reverse engineering

- Requirements recovery

- Expert interviews

- Knowledge transfer

- Business-rule discovery

- Architecture design

- Data mapping

- Data migration

- Integration development

- Parallel testing

- Financial reconciliation

- Security testing

- Performance testing

- Compliance validation

- Cutover planning

- Rollback preparation

- Documentation

- Training

Therefore, LOC is not a direct measure of migration effort.

# 30. Quality Management

Quality will be built into every project phase.

### Requirements Quality

Requirements must be:

- Complete

- Consistent

- Testable

- Traceable

- Approved

### Design Quality

Architecture must be reviewed for:

- Scalability

- Reliability

- Security

- Maintainability

- Integration

- Migration compatibility

### Code Quality

Code should undergo:

- Peer review

- Static analysis

- Unit testing

- Integration testing

- Security testing

### Migration Quality

Migration must be validated through:

- Data reconciliation

- Parallel execution

- Automated comparisons

- Product-specific testing

- EOD validation

# 31. Requirements Traceability

Every important requirement should be traceable through the project.

The traceability chain will be:

Requirement → Design → Implementation → Test Case → Test Result → Approval

For example:

Interest Calculation Requirement

→ Interest Service Design

→ Interest Calculation Implementation

→ Interest Test Cases

→ Legacy vs Modern Comparison

→ Reconciliation Result

→ Business Approval

This ensures that no critical business rule is lost during migration.

# 32. Knowledge Management

A dedicated knowledge repository will be maintained.

It should contain:

- COBOL module descriptions

- Business rules

- Data mappings

- EOD procedures

- Product rules

- Exception cases

- Architecture decisions

- Meeting decisions

- Test evidence

- Reconciliation results

- Cutover documentation

- Rollback procedures

All important knowledge should be documented rather than remaining only in individual employees’ memory.

# 33. Configuration Management

All project artifacts should be version controlled.

This includes:

- Source code

- Requirements

- Architecture documents

- Database scripts

- Configuration files

- Test cases

- Test results

- Migration scripts

- Deployment scripts

- Runbooks

Production configuration must be controlled separately from development configuration.

# 34. Security Management

Security must be considered throughout the project rather than only before production.

The project will implement:

- Role-based access

- Authentication and authorization

- Encryption

- Secure APIs

- Audit logs

- Vulnerability testing

- Access monitoring

- Secure secrets management

- Incident response procedures

Sensitive banking data should not be exposed unnecessarily during testing.

# 35. Cutover Management

The final cutover will be controlled through a formal runbook.

### T-7 Days

- Conduct final rehearsal.

- Validate rollback.

- Verify backups.

- Confirm staffing.

- Confirm monitoring.

### T-24 Hours

- Complete final backup.

- Confirm system health.

- Confirm reconciliation readiness.

- Freeze non-essential changes.

### T-1 Hour

- Verify target system.

- Verify infrastructure.

- Verify monitoring.

- Verify database connectivity.

### T-30 Minutes

- Freeze critical transactions according to the approved operational procedure.

- Perform final reconciliation.

- Confirm go/no-go status.

### T = 0

- Switch approved production traffic.

- Monitor transaction processing.

### T+15 Minutes

- Check transaction success.

- Check errors.

- Check system health.

### T+30 Minutes

- Perform focused reconciliation.

- Verify critical products.

- Confirm operational stability.

# 36. Rollback Management

Rollback must be planned before cutover.

Rollback will be initiated if a predefined critical condition occurs.

Possible rollback triggers include:

- Unexplained financial divergence.

- Critical transaction failure.

- Major data corruption.

- Security incident.

- Severe performance failure.

- Loss of critical functionality.

- Failure of reconciliation controls.

The rollback process should include:

- Stop affected modern processing.

- Preserve logs and evidence.

- Restore or continue the approved legacy processing path.

- Reconcile affected transactions.

- Investigate the root cause.

- Correct the problem.

- Repeat testing.

- Schedule another controlled cutover.

# 37. Go/No-Go Decision

The final migration will use a formal Go/No-Go meeting.

### Go Criteria

The migration can proceed only when:

- Critical requirements are approved.

- Critical defects are resolved.

- Data migration is validated.

- Parallel-run results are satisfactory.

- No unexplained monetary differences remain.

- Backup and rollback have been tested.

- Monitoring is operational.

- Security checks are complete.

- Required stakeholders have approved.

- Operations team is ready.

### No-Go Criteria

Migration must be stopped if:

- Critical financial discrepancies remain.

- Critical defects remain unresolved.

- Data integrity is uncertain.

- Rollback has not been tested.

- Required approvals are missing.

- Monitoring is unavailable.

- Production readiness criteria are not satisfied.

# 38. Project Governance

A three-level governance structure will be used.

## Level 1 – Project Team

Handles:

- Development

- Testing

- Requirements

- Technical issues

- Daily activities

## Level 2 – Project Management

Handles:

- Schedule

- Resources

- Risks

- Issues

- Scope

- Dependencies

## Level 3 – Steering Committee

Handles:

- Major financial decisions

- Major scope changes

- Critical risks

- Cutover approval

- Major escalations

# 39. Steering Committee

The Steering Committee should contain representatives from:

- Bank Management

- Project Sponsor

- Project Manager

- Business/Product Team

- Technology Team

- Risk/Compliance

- Operations

The Steering Committee should meet at major milestones and whenever a critical decision is required.

# 40. Project Success Criteria

The CoreShift project will be considered successful when:

- The modern system replaces the required legacy functionality.

- Critical business rules have been recovered and documented.

- Legacy knowledge has been transferred from retiring experts.

- Data has been successfully migrated.

- Parallel-run testing has been completed.

- Product Type 14 has been tested across all 30 accounts.

- Financial calculations match the legacy system.

- There are zero unexplained monetary differences at final approval.

- Security and compliance requirements are satisfied.

- Production cutover is completed successfully.

- Rollback capability has been verified.

- The modern system can be supported without dependence on the retiring COBOL experts.

# 41. Final Management Dashboard

The Project Manager should maintain a dashboard containing at least the following:

### Project Status

- Overall project percentage

- Current phase

- Next milestone

- Schedule status

### Migration

- Accounts migrated

- Accounts compared

- Accounts matching

- Accounts under investigation

- Unexplained monetary variance

### Quality

- Open defects

- Critical defects

- Defect density

- DRE

- Test pass percentage

### Risk

- Critical risks

- High risks

- Newly identified risks

- Risk trend

### Knowledge Transfer

- Expert sessions completed

- Business rules recovered

- Modules documented

- Replacement staff trained

### Cutover Readiness

- Backup status

- Rollback status

- Monitoring status

- Security status

- Reconciliation status

- Business approval status

# 42. Conclusion

CoreShift will be managed as a controlled, high-risk banking modernization project rather than as a simple code conversion exercise.

The project will combine reverse engineering, requirements recovery, incremental development, parallel testing, automated reconciliation, risk management, formal governance and controlled cutover.

The most important management principle is that modernization must not compromise financial correctness.

The four legacy experts will be treated as critical knowledge resources, and their knowledge will be captured before retirement. The development team will build the modern system incrementally, while the QA and reconciliation teams will continuously compare the new system against the trusted legacy baseline.

The Strangler-Fig migration strategy will prevent the risks associated with a big-bang replacement. The legacy system will remain available while functionality is gradually transferred to the modern architecture.

Final production migration will occur only after technical, business, security, operational and reconciliation criteria have been satisfied.

The ultimate success condition is:

Modernized system + preserved business behaviour + zero unexplained monetary divergence + controlled cutover + tested rollback capability.